## Slide 1: Scheduling

## Slide 2: Module 2 Detailed Schedule
 |  |  |  |  |  |  |  |  |  |  |  | Hand in
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Milestone | Unit Introduction | Client Briefing | Present Charter | Review Draft Analysis | Present Analysis | Ideation Phase | Solution Selection | Solution Selection | Solution Presentation |  |  | Project evaluation
Aim | Set The Ground Rules | Understand Assignment Brief | To present/ refine team charters | To Refine Analysis/ Analysis Outcomes | To formally present analysis process/ outcomes | To identify practical solution(s) | Initial evaluation of proposed solutions | Final evaluation of proposed solutions | Formal Presentation of Final Proposals |  |  | Giving feedback
Activities/ Roles | EL, +2 Support Provide Intro/ Overview | PoPs Present Brief(s) Student Q&A Students Form Teams & Start To Draft Charters | Students Present Charters EL, +2 Support Present Problem Analysis Methods | EL, +2 Support Discuss Analysis With Students | Pops/ EL Host Review Panel Students present analysis/ explore potential options with Panel | EL, +2 Support facilitate ideas generation Students generate alternative/ refined solutions | EL, +2 Support to provide evaluation methods | EL, +2 Support to provide evaluation methods | Pops/ EL Host Review Panel Students present proposals to Panel |  |  | 
Outcomes | Students Understand: UIF Their Responsibilities | Students have sufficient Information to Draft Team Charters | Agreed/ Final Charter Knowledge of Analysis Tools | Refined analysis | Documented/ Complete Analysis | Short list of justified/ practical solutions | Evaluated solutions | Evaluated solutions | Assessed Proposals |  |  | Feedback session
Support Materials | UIF?? | Client Briefing Pack | Charter Pro-Forma Analysis Methods | Presentation Pro-Forma? |  | Ideas Creation Pack? | Evaluation Tools Pack? |  |  |  |  | 
Assessments |  |  |  |  | Charter Analysis |  |  |  | Proposal |  |  | 
TBD
- How to manage weekly activity…drop ins?

## Slide 3: Module 1 Detailed Schedule
5/10 | 12/10 | 19/10 | 26/10 | 2/11 | 9/11 | 16/11 | 23/11 | 30/11 | Hand in
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Introduction to the unit | Presentation of the project brief | Present charter | Problem analysis | Present analysis | Ideation phase | Solution selection | Solution selection | Solution presentation | Project evaluation
Ground rules |  |  | Discuss | Panel feedback (+ prof) | Challenge solutions |  |  | Panel feedback | Giving feedback
Teams | Professors of Practice | Problem analysis methods | Redefinition? |  | Generate alternatives | Evaluation methods |  |  | 
Staff | PoPs Present Brief | EL + 2 Support Manage Discussion | EL + 2 Support Manage Discussion | Potential solutions |  |  | Process evaluation methods |  | Feedback session
Students | Understanding the assignment brief |  |  |  |  |  |  |  | 
Activity | Student prep charters | Students Start analysis | Students Refine Analysis | Ideation methods |  |  |  |  | 
EL + 2 Support | PoPs EL +2 Support | EL + 2 Support | EL + 2 Support | PoPs EL +2 Support | EL + 2 Support | EL + 2 Support | EL + 2 Support | PoPs EL +2 Support | 

## Slide 4: Weeks 0-10
5/10 | 12/10 | 19/10 |  |  |  |  |  |  | 
0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Review Brief
Select Team
Document Charter
Analyse Problem
Present
Charter
Present
Analyse
Define Potential Solution Options
Select
Solution
‘Define’
‘Analyse’
‘Design’
‘Delivery’
Define Implementation Approach (Risks, Impact, Timelines, Resources, etc.)
Select
Solution
‘Review’
Review
  Adherence to Charter
  Roles and Responsibilities
  360’s
  What would you do differently again?
Post Project
Review