## Slide 1: Managing Projects
RACI

## Slide 2: Responsible Accountable Consulted Informed

## Slide 3: Sourcing Projects
Alumni: 20%
Repeats: 40%
Internal: 10%
New contact: 30%
  Largely untested but alumni are asking to participate.
  Social Media campaign starting to attract alumni.
  We run two internal projects this year, one with HRM department and the other with the Partnership Office.
  Initial analysis followed by implementation.
  Source from ongoing external engagement work
  Larger companies beginning to engage
  Steady stream from Careers and Employability
  Target is 200 engaged alumni by July 2014
  Many local alumni are now in senior positions
  Our relationship with clients is more stable.
  Opens opportunities for commercial relationships
  Clients start to look at other opportunities across Faculty
  Good rapport, builds internal awareness of UBBS mission.
  Internal departments spot talent
  Low-risk initial engagement for clients
  Build rapport quickly with lead to commercial work.
  Why? Benefits/Outputs
  From the pilots in 2013, all companies wanted to repeat with a new project
  Repeats are more likely to generate multiple projects

## Slide 4: Approach
Engage (-3 months)
Design (-1 month)
Deliver
Review (+1 week)
  New\existing clients
  Document client problem and expectations (deliverables and timescales)
  Fix\commit resources (facilitators\rooms\etc)
  Document Pre-practice week materials
  Identify student groups
  Document launch presentations
  Deliver Practice Week
  Clients to declare expectations met
  Students to review event\lessons learnt
  Practice week co-ordinators employ lessons learnt
  Produce long term client engagement ‘plan’
  Review students who have joined client (?)
  Client contact details registered centrally
  Proposal Template completed
  NDA Signed
  Branding agreement signed?
  Named Resources
  Named Student teams and allocated projects
  Rooms booked
  Proposal Template and Supporting documents available to students (BREO?)
  Schedule agreed/available on BREO
  Attendance list available
  Launch slides available on BREO
  Launch sessions completed
  Students mobilised
  Attendance taken
  Daily updates completed
  Final Client meeting booked and prepared
  Client meeting complete
  Client feedback/assessment completed
  Clients to declare expectations met
  Students to review event\lessons learnt
  Practice week co-ordinators employ lessons learnt
  Produce long term client engagement ‘plan’
  Review students who have joined client (?)
  Outputs

## Slide 5: Governance \ Roles
Board
Account Manager
Practice Week Manager
Project Manager
Administrators
 | Engage |  | Design |  |  |  | Deliver |  |  |  | Review\Maintain |  |  | 
 | Identify\ Agree Client(s) and Add to Register | Approach Client\ Agree Collaboration (Principles) | Agree and Set PW Project Slots | Secure Rooms \ Book Resources | Draft and Approve Project Proposals | Select\ Group Students | Conduct PW Pre-Brief | Ensure Client Available\ Ready | Host Client\ Student Briefings | Assess Student Performance | Close Project with Client and Draft Long Term Client Engagement Plan | Complete Student Feedback Sessions | Manage Student Placements | Complete ‘Lessons Learnt’
 | A | A | A | I | I | I | A | I | I | A | C | I | A | I
Account Manager | R | R | C | I | C | I | R | C | C | C | R | C | R | R
PW Manager | C | C | R | A | A | R | R | A | C | R | C | R | C | A/R
Admin | I | I | R | R | C | I | R | I | C | I | C | C | I | R
Project Manager | I | I | I | C | R | C | R | R | R | C | C | R |  | R