## Slide 1
Web Design and Development
Principles of Project Management
Tim Priestman
7th December 2013

## Slide 2: What is a project?
What’s the difference?
Operational Work
Project Work

## Slide 3: What is a project?
Operational Work – repetitive tasks – often not subject to change
Project Work – unique and one-off – about change – made up of activities (some parallel) and dependencies and

## Slide 4: Definition
“ An undertaking which, via a series of planned activities is designed to achieve a particular objective by a particular time.”

## Slide 5: Project Lifecycle
Concept
Definition
Implementation
Handover
Closeout

## Slide 6: Concept Stage
Is it possible?
Technically
Commercially
Risk
http://www.hfl.co.uk/content/what-we-stand

## Slide 7: Definition Phase
Feasibility Study
Cost benefit appraisal and risks
Authorisation and appointment of the project team
http://www.risk-doctor.com

## Slide 8: Tools for Identifying Risk
Look at project concerns - subjective
SWOT analysis
PEST - political, economic, social and technical

## Slide 9: Implementation Phase
There is a cycle of:
Plan
Monitor
Control
This is a continuous process.

## Slide 10: Handover & Closeout
Deliverables moved to operational management structure
Final reports such as post project review

## Slide 11: The Project Environment
The context of your project

## Slide 12: Projects, programmes & portfolios

## Slide 13: Projects, programmes & portfolios
Projects are finite
Programmes focus on broader benefits being delivered
Programmes focus on external environment, cultural and social impacts
Programmes are increasingly being user to manage large scale change

## Slide 14: PESTLE
Political
Economic
Social
Technical
Legal
Environmental

## Slide 15: Stakeholders
Impact
Importance
Low
High
High
Project Sponsor

## Slide 16: Business Case
Why is it needed
Options
Benefits
Risks
Cost and Timescale

## Slide 17: The Project Board

## Slide 18: Planning a Project

## Slide 19: Planning a Project
The Project Management Plan
Product Breakdown (like WBS) what are the products (deliverables) required to produce the larger product?
Assign resource (person) – person is responsible for product description – what is it (quality) why do we need it?

## Slide 20: Product Flow Diagram
The sequence that shows how the product is developed
Leads on to Activity based WBS

## Slide 21: Activity List
ID | Activity | Dur. | Dep.

## Slide 22: Project Management Plan
Introduction and Summary
Statement of Acceptance.
Work breakdown structures
Schedule

## Slide 23: Tools available
Meetings
Reports
Sign-offs
Project management tools

## Slide 24: Milestones & deliverables
Points between phases - take stock and adjust
items are developed, reviewed and released (may be paper or elect.)
keep the project on track
allow for minor changes

## Slide 25: Exercise
Look at the project cycle.
Identify the key deliverables and milestones.
What will they be for your project?
How does this relate to risk containment?

## Slide 26: Risk Management
should take place throughout the project
management processes reduce or eliminate risk
risks can be categorised

## Slide 27: Risk Management – What are the risks?

## Slide 28: Tools for Identifying Risk
Look at project concerns - subjective
SWOT analysis
PEST - political, economic, social and technical

## Slide 29: Exercise
Where would you expect the main risks to arise in the life-cycle?
How would you categorise them?
What are the barriers to success?
Apply those categories to your own project

## Slide 30: Breakdown Structures
Work (WBS)
Organisation (OBS)
Cost (CBS)
Location (LBS)
Resources (RBS)

## Slide 31: Work breakdown structure
project phases
divided into work disciplines (marketing, design)
divided into products – to fulfil discipline
Products divided into work required to complete – work packages

## Slide 32: Why breakdown structures?
Identifies work required for each output (work package)
helps in planning
helps in costing

## Slide 33: A Work Package
comprises one action
performance is measurable
is a manageable chunk
is unlikely to be interrupted

## Slide 34: A Work package
cost and time is predictable
is owned by one person
requires the same resource throughout
May be critical or non-critical

## Slide 35: Exercise
Take one part of your project and follow the diagram to create a work package
Exchange with a colleague to review.

## Slide 36: Microsoft Project
Enables rapid adjustment
Clear project representation
good presentation tool - at different levels of detail

## Slide 37: Exercise
Take one work package from your project. Put it into Microsoft project - use either Module 2 or 3
Review with a colleague