## Sheet1
Workstream | Action | Who | Dependency | Who? | Completion Date
Event Management | Agree Date | David/Stephen
Event Management | Agree Venue | David/Stephen
Event Management | Book rehearsal time | David/Stephen
Event Management | Agree event title | Stephen
Event Management | Agree event content and schedule | Stephen
Event Management | Agree Guest Host | David/Stephen | N Owen | Tim
Event Management | Book Pre Event Drinks | David/Stephen |  | Tim
Event Management | Book Post Event Food & Drinks | David/Stephen |  | Tim
Event Management | Create Pre-Film Audience Name List Handout | David/Stephen |  | CB/KP
Event Management | Agree event manager | David/Stephen
Event Management | Agree budget for event | Stephen | Content agreed | Tim
Event Management | Book Vision/Sound/Lights | David/Stephen |  | Tim
Event Management | Create Reception Displays (Posters\Films\Other) | David/Stephen
Event Management | Finalise Name Badges | David/Stephen |  | CB/KP
Event Management | Agree Man-Marking Plan (VIPs) | David/Stephen
Event Management | Create Post Event Leaving Packs | David/Stephen
Event Management | Set up Live Web Broad Cast/Tweet Messaging | David/Stephen
| Prepare room for event with banners, posters etc | David/Stephen
Event Management | Produce DVDs for distribution to partners | David/Stephen
Event Management | Debrief session | David/Stephen |  | Tim
| Follow-up actions after event | David/Stephen
Client and Student Management | Identify and Secure 2 Clients | Bill/Tim
Client and Student Management | Identify and Secure 2 Student Groups | Bill/Tim
Client and Student Management | Secure film crew | Bill/Tim
Client and Student Management | Agree film story board | Bill/Tim/Tricia
Client and Student Management | Agree Project Briefs with Clients | All?
Client and Student Management | Conduct Student Team Building | Bill/Tim
Client and Student Management | Studnets Conduct Compnay Background | Bill/Tim
Client and Student Management | Manage client/student engagement | Bill/Tim
Client and Student Management | Students to document project\diary\learning journey | Bill/Tim
Client and Student Management | Manage film crew | Bill/Tim
Marketing | Finalise event name | Colin/KP
Marketing | Create marketing plan (who\what\when) | Colin/KP
Marketing | Finalise event market messages | Colin/KP
Marketing | Identify Stakeholder Groups and Messages | Colin/KP
Marketing | Finalise target attendee list | Colin/KP
Marketing | Create marketing materials (web sites\posters/leaflets/flyers) | Colin/KP
Marketing | Issue tickets | Colin/KP
Marketing | Progress non-ticket returns? | Colin/KP